## Board
Item | Type | Status | Subject | Grades | Cases done | Cases planned | Priority | Blocked by | Next action | Notes
Group Chat | Engine | Live | All subjects | 3-5 | 8 | 27 | Low |  | Decide whether the 19 older cases are still wanted | 8 published. 19 more were built in the old paper era and never converted for the app.
Signal Check | Engine | Live | All subjects | 3-5 | 108 | 108 | Medium |  | Confirm the Social Studies database changes actually ran | 84 Science and Social Studies standards, plus 24 Math and ELAR cases added 21-22 Sept. Three dead files still need deleting.
Mission Map | Engine | Live | All subjects | 3-5 | 37 | 49 | High |  | Author the ELAR 12 | Science 13/13, Social Studies 12/12, Math 12/12 as of 23 Sept. ELAR is the only remaining gap and its standards are already approved.
Simulation Lab | Engine | Needs testing | Science | 3-5 | 10 | 10 | Medium |  | Run the 10 cases with a student, then generate their artwork | Two real bugs were found the last time this was tested with a student. Nothing has been tested since.
Frequency Rush / Signal Ops | Engine | Live | All subjects | 3-5 |  |  | Low |  | None | Vocabulary practice engine plus the whole-class Signal Ops board.
Relay Station | Engine | Needs testing | ELAR | 3-5 | 94 | 94 | Medium |  | Run Waves 2 and 3 with a student | Typing centre that doubles as reading practice: a 20-level track, 72 readings, and a whole-class race. Waves 2 and 3 have only been checked by simulation.
Assembly Deck | Engine | Needs testing | All subjects | 3-5 | 6 | 54 | High |  | Re-run one case with a student now the new ending is in | Piloted successfully with a grade 3 student on 23 Sept. That pilot produced two changes: a Case File students can open on any screen, and a new two-question debrief. 48 further cases are mapped and standards-checked.
Classification Lab | Engine | Not started | Not subject-specific | 3-5 | 0 | 0 | Low |  | Decide whether it is still wanted | Designed 29 Aug. Never built.
Repair Desk | Engine | Not started | Not subject-specific | 3-5 | 0 | 0 | Low |  | Decide whether it is still wanted | Designed 29 Aug. 11 cases exist from the old paper era.
Field Dispatch | Engine | Not started | Not subject-specific | 3-5 | 0 | 0 | Low | Needs original artwork for every single case | Decide whether it is still wanted | The only planned engine that cannot reuse artwork between cases.
The Tribunal | Engine | Not started | Not subject-specific | 3-5 | 0 | 0 | Low |  | Decide whether it is still wanted | Designed 29 Aug. Never built.
Newsroom | Engine | Not started | Not subject-specific | 3-5 | 0 | 0 | Low |  | Decide whether it is still wanted | 38 cards exist from the old era, but they were written against a design that was later rejected.
Mission Map - Math 12 | Content batch | Done | Math | 3-5 | 12 | 12 | High |  | None - shipped 23 Sept | Closed a gap that had been open since August, waiting on official standards documents.
Mission Map - ELAR 12 | Content batch | Ready to start | ELAR | 3-5 | 0 | 12 | High |  | Author the 12 cases | Standards already checked against the official ELAR document and approved. Nothing is blocking this.
Assembly Deck - ELAR 12 | Content batch | Blocked | ELAR | 3-5 | 0 | 12 | Medium | The 48-case plan has not been reviewed yet | Review the 48-case plan | First of four planned batches.
Assembly Deck - Science 12 | Content batch | Blocked | Science | 3-5 | 0 | 12 | Medium | The 48-case plan has not been reviewed yet | Review the 48-case plan
Assembly Deck - Social Studies 12 | Content batch | Blocked | Social Studies | 3-5 | 0 | 12 | Medium | The 48-case plan has not been reviewed yet | Review the 48-case plan
Assembly Deck - Math 12 | Content batch | Blocked | Math | 3-5 | 0 | 12 | Medium | The 48-case plan has not been reviewed yet | Review the 48-case plan | This batch also needs a scratch pad added to the student screen.
Test flag still unlocks everything | Risk | Not started | Not subject-specific |  |  |  | High |  | Switch the flag off | Every planet in the Galaxy Hub is currently unlocked for every student. This has to be switched off before the site is used with a real class.
Three engines have never been tested with students | Risk | Not started | Not subject-specific |  |  |  | High |  | Book time to run each one | Assembly Deck since its redesign, Relay Station Waves 2 and 3, and Simulation Lab's 10 cases.
Older content never checked for reading level | Risk | Not started | All subjects | 3-5 |  |  | Medium |  | Decide whether to run the checker over it | Frequency Rush, Signal Check, Simulation Lab and the Briefings were all written before the grade-level checker existed.
Mission Map's original 25 cases read above grade | Risk | Not started | All subjects | 3-5 |  |  | Medium |  | Decide whether to rewrite them | Measured 23 Sept. The grade 3 cases read at a 5.8 reading level against a 4.2 ceiling, and the three grades barely differ from one another.
Older database changes never confirmed | Risk | Not started | Not subject-specific |  |  |  | Medium |  | Check each one against the live database | Simulation Lab, Mission Map's September batch and Signal Check's Social Studies batch were never verified after the changes were written.
Assembly Deck has no artwork of its own | Art | Not started | Not subject-specific |  |  |  | Medium |  | Generate the tile image | The engine is currently displaying the Repair Desk picture. Nothing is broken; it is just wearing another engine's artwork.
Relay Station artwork not connected | Art | Not started | ELAR | 3-5 |  |  | Low | Nobody knows which folder the generated files went into | Locate the generated files | Rank badges, keyboard skin previews, and the posture and hand-position diagrams.
Case thumbnails missing | Art | Not started | All subjects | 3-5 |  |  | Low |  | Generate the remaining images | 63 Relay Station readings and all 10 Simulation Lab cases still have no thumbnail.

## How to import this
Importing this into monday.com
1. In monday.com, click your profile picture (top right), then Import Data, then Excel.
2. Upload this file, or upload the .csv version if monday asks which sheet to use.
3. When it asks which row holds the column titles, choose row 1.
4. Check the column types it suggests before you finish - see the note below.
About the column types
monday guesses a column's type from its contents. A column with 9 or fewer different
values becomes a coloured Status column; more than 9 and it becomes plain text.
This sheet was built to stay under that limit, so Type, Status, Subject, Grades and
Priority should all come through as coloured Status columns automatically.
Cases done and Cases planned should come through as Number columns. If they do not,
change them by hand - monday can then show a progress bar and totals.
After the import
Everything will land in a single group. To split it up, use Group by at the top of the
board and group by Type - that gives you Engines, Content batches, Risks and Art.
The limits, if you ever import a bigger file: 10MB, 8,000 rows and 100 columns for a
new board, and a Status column cannot have more than 40 different values.
Where this came from
Every row was taken from ClearCenters_STATE.md as it stood on 23 September 2026.
The counts are real: 37 Mission Map cases, 6 Assembly Deck cases, 94 Relay Station
lessons. Blank cells in Cases done and Cases planned mean the row is not a content
batch and a count would not mean anything.